## Sheet1
ID | Requirements | Priority | Days
1 | As the Managing Director I want a monthly report showing the percentage of belts that have been sold via the Web site so that I can get a feel for the benefits, in terms of profit, that we are getting from the Web site. | Should Have | 3
2 | As a customer I want to be able to modify my shopping cart so that I can change my mind about what I want to buy. | Must Have | 5
3 | As a Customer I want to enter separate delivery and invoice addresses so that I can receive belts when staying at a friend’s house. | Could Have | 3
4 | As the Finance Director I want all online transactions to be secure so that our customers feel safe. | Must Have | 6
5 | As the Managing Director I want to be ensured that the site is Data Protection Act safe so that we do not get fined hundreds of thousands of pounds. | Must Have | 8
6 | As the Marketing Director I want an ‘About Page’ so that we can promote the finer details of the brand. | Should Have | 3
7 | As a Customer I want a choice of delivery slots so that I can arrange my diary appropriately. | Could Have | 5
8 | As the Warehouse Manager I want to place an ‘out of stock’ message on appropriate belts so that customers do not end up having to wait for ages due to belts being out of stock. | Must Have | 5
9 | As the Operations Director I want to accept all forms of payment so that we can capture the largest market possible. | Must Have | 5
10 | As a Customer I want to choose whether or not I am sent marketing information so that I do not get loads of junk mail. | Should Have | 2
11 | As a Warehouse Operative I want to check delivery addresses so that I can place orders with similar postcodes in the same delivery batch. | Should Have | 3
12 | As a Customer I want to be able to change my account details so that my most up to date details are recorded. | Should Have | 3
13 | As an Order Handling Clerk I want to use the Web site to process telephone purchases so that I can stop using the paper-based system. | Should Have | 2
14 | As a Customer I want to have belts gift wrapped and sent to an address other that than my own so that I don’t have to bother wrapping and delivering presents. | Won’t have | 4
15 | As a Student I want discounts on belts so that I can look cool at parties for minimal cost. | Won’t have | 3
16 | As a Customer I want to be sent an SMS message to remind me when my belts are going to be delivered so that I am in when they arrive. | Could Have | 3
17 | As a Customer I want daily emails to let me know the status of my order because I get nervous when I don’t know what is going on. | Could Have | 4
18 | As the Marketing Director I would like an offers or discount page so that we can inform our customers of the aforementioned. | Could Have | 3
19 | As the Chief Accountant I want to the Web site to adhere to legislation regarding VAT so we are not hit with a hefty fine. | Must Have | 2
20 | As a customer I want to be able to process returns via the Web site so that I do not have to phone up and answer all of those stupid questions before being put through to a human being. | Won’t have | 4
Total: 73 days
| Less than 60% | Must Have | 33 days | Less than 80%
| Can be > 20% | Should Have | 11 days
| Can be > 20% | Could Have | 11 days
|  | Won’t have | 17 days